## Project Plan (Part-time)
Task | Description | Start Date | End Date | Responsible | Status | Effort (Hours) | Duration (Days) | Dependencies
Project Kickoff | Confirm scope and success criteria | 2026-01-05 | 2026-01-06 | Wisawa | Planned | 4 | 2
Requirements & Constraints | Define throughput/latency targets, UART baud | 2026-01-07 | 2026-01-10 | Wisawa | Planned | 10 | 4
System Architecture | Blocks: TDC7200 IF, acquisition, FIFO, UART | 2026-01-11 | 2026-01-14 | Wisawa | Planned | 10 | 4
Clocking & Timing Strategy | PLL/MMCM, sampling schedule | 2026-01-15 | 2026-01-18 | Wisawa | Planned | 12 | 4
TDC7200 Interface Design | Control + measurement read sequence | 2026-01-19 | 2026-01-29 | Wisawa | Planned | 28 | 11
High-Rate Acquisition Core | Pipelined capture, burst mode | 2026-01-30 | 2026-02-08 | Wisawa | Planned | 32 | 10
Buffering (FIFO) | Dual-clock FIFO, overflow handling | 2026-02-09 | 2026-02-15 | Wisawa | Planned | 20 | 7
UART Framing & Flow Control | Packet headers, CRC, tune baud | 2026-02-16 | 2026-02-22 | Wisawa | Planned | 20 | 7
Top-Level Integration | Integrate modules + diagnostics | 2026-02-23 | 2026-03-01 | Wisawa | Planned | 16 | 7
HDL Testbench & Simulation | Sensor-read TB, stress tests | 2026-03-02 | 2026-03-13 | Wisawa | Planned | 30 | 12
Synthesis & Timing Closure | Constraints, reports | 2026-03-14 | 2026-03-18 | Wisawa | Planned | 16 | 5
FPGA Implementation | Place/Route, pins, bitstream | 2026-03-19 | 2026-03-23 | Wisawa | Planned | 16 | 5
Board Bring-up | Program FPGA, verify comms | 2026-03-24 | 2026-03-29 | Wisawa | Planned | 16 | 6
Python API Design | Packet parser, plotting hooks | 2026-03-30 | 2026-04-04 | Wisawa | Planned | 14 | 6
Python UART I/O & Visualization | pyserial I/O, live charts | 2026-04-05 | 2026-04-11 | Wisawa | Planned | 20 | 7
Throughput Tuning | Tune FIFOs & UART, benchmark | 2026-04-12 | 2026-04-18 | Wisawa | Planned | 16 | 7
Validation & Debugging | Corner cases, reliability | 2026-04-19 | 2026-04-25 | Wisawa | Planned | 16 | 7
Documentation & Handover | Design/user guide, API ref | 2026-04-26 | 2026-04-30 | Wisawa | Planned | 12 | 5

## Work Calendar
Date | Day | Hours
2026-01-05 | Mon | 2
2026-01-06 | Tue | 2
2026-01-07 | Wed | 2
2026-01-08 | Thu | 2
2026-01-09 | Fri | 2
2026-01-10 | Sat | 5
2026-01-11 | Sun | 5
2026-01-12 | Mon | 2
2026-01-13 | Tue | 2
2026-01-14 | Wed | 2
2026-01-15 | Thu | 2
2026-01-16 | Fri | 2
2026-01-17 | Sat | 5
2026-01-18 | Sun | 5
2026-01-19 | Mon | 2
2026-01-20 | Tue | 2
2026-01-21 | Wed | 2
2026-01-22 | Thu | 2
2026-01-23 | Fri | 2
2026-01-24 | Sat | 5
2026-01-25 | Sun | 5
2026-01-26 | Mon | 2
2026-01-27 | Tue | 2
2026-01-28 | Wed | 2
2026-01-29 | Thu | 2
2026-01-30 | Fri | 2
2026-01-31 | Sat | 5
2026-02-01 | Sun | 5
2026-02-02 | Mon | 2
2026-02-03 | Tue | 2
2026-02-04 | Wed | 2
2026-02-05 | Thu | 2
2026-02-06 | Fri | 2
2026-02-07 | Sat | 5
2026-02-08 | Sun | 5
2026-02-09 | Mon | 2
2026-02-10 | Tue | 2
2026-02-11 | Wed | 2
2026-02-12 | Thu | 2
2026-02-13 | Fri | 2
2026-02-14 | Sat | 5
2026-02-15 | Sun | 5
2026-02-16 | Mon | 2
2026-02-17 | Tue | 2
2026-02-18 | Wed | 2
2026-02-19 | Thu | 2
2026-02-20 | Fri | 2
2026-02-21 | Sat | 5
2026-02-22 | Sun | 5
2026-02-23 | Mon | 2
2026-02-24 | Tue | 2
2026-02-25 | Wed | 2
2026-02-26 | Thu | 2
2026-02-27 | Fri | 2
2026-02-28 | Sat | 5
2026-03-01 | Sun | 5
2026-03-02 | Mon | 2
2026-03-03 | Tue | 2
2026-03-04 | Wed | 2
2026-03-05 | Thu | 2
2026-03-06 | Fri | 2
2026-03-07 | Sat | 5
2026-03-08 | Sun | 5
2026-03-09 | Mon | 2
2026-03-10 | Tue | 2
2026-03-11 | Wed | 2
2026-03-12 | Thu | 2
2026-03-13 | Fri | 2
2026-03-14 | Sat | 5
2026-03-15 | Sun | 5
2026-03-16 | Mon | 2
2026-03-17 | Tue | 2
2026-03-18 | Wed | 2
2026-03-19 | Thu | 2
2026-03-20 | Fri | 2
2026-03-21 | Sat | 5
2026-03-22 | Sun | 5
2026-03-23 | Mon | 2
2026-03-24 | Tue | 2
2026-03-25 | Wed | 2
2026-03-26 | Thu | 2
2026-03-27 | Fri | 2
2026-03-28 | Sat | 5
2026-03-29 | Sun | 5
2026-03-30 | Mon | 2
2026-03-31 | Tue | 2
2026-04-01 | Wed | 2
2026-04-02 | Thu | 2
2026-04-03 | Fri | 2
2026-04-04 | Sat | 5
2026-04-05 | Sun | 5
2026-04-06 | Mon | 2
2026-04-07 | Tue | 2
2026-04-08 | Wed | 2
2026-04-09 | Thu | 2
2026-04-10 | Fri | 2
2026-04-11 | Sat | 5
2026-04-12 | Sun | 5
2026-04-13 | Mon | 2
2026-04-14 | Tue | 2
2026-04-15 | Wed | 2
2026-04-16 | Thu | 2
2026-04-17 | Fri | 2
2026-04-18 | Sat | 5
2026-04-19 | Sun | 5
2026-04-20 | Mon | 2
2026-04-21 | Tue | 2
2026-04-22 | Wed | 2
2026-04-23 | Thu | 2
2026-04-24 | Fri | 2
2026-04-25 | Sat | 5
2026-04-26 | Sun | 5
2026-04-27 | Mon | 2
2026-04-28 | Tue | 2
2026-04-29 | Wed | 2
2026-04-30 | Thu | 2

## Gantt Chart
Task | Start Date | End Date | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
Project Kickoff | 2026-01-05 | 2026-01-06
Requirements & Constraints | 2026-01-07 | 2026-01-10
System Architecture | 2026-01-11 | 2026-01-14
Clocking & Timing Strategy | 2026-01-15 | 2026-01-18
TDC7200 Interface Design | 2026-01-19 | 2026-01-29
High-Rate Acquisition Core | 2026-01-30 | 2026-02-08
Buffering (FIFO) | 2026-02-09 | 2026-02-15
UART Framing & Flow Control | 2026-02-16 | 2026-02-22
Top-Level Integration | 2026-02-23 | 2026-03-01
HDL Testbench & Simulation | 2026-03-02 | 2026-03-13
Synthesis & Timing Closure | 2026-03-14 | 2026-03-18
FPGA Implementation | 2026-03-19 | 2026-03-23
Board Bring-up | 2026-03-24 | 2026-03-29
Python API Design | 2026-03-30 | 2026-04-04
Python UART I/O & Visualization | 2026-04-05 | 2026-04-11
Throughput Tuning | 2026-04-12 | 2026-04-18
Validation & Debugging | 2026-04-19 | 2026-04-25
Documentation & Handover | 2026-04-26 | 2026-04-30